## Sprint 1
Backlog - Sprint 1
Duration 29/10/18 To 12/11/18
| Status Levels: | People: | Effort Points |  |  |  | Individual Hrs: | Group Hrs:
| Committed | Callum Sellick | 1 - Within a day |  |  |  | 6 hours a week | 24 hrs
| In-progress | Kieran Bourne | 2 - Two days
| Done | Bogdan-Stefan Pop | 3 - More than 2
Thomas Hughes
ID: | Task: | Assigned To: | Effort Points: | Estimated Hours: | Status: | Signatures:
1 | Create a sprint document to record progress. | Callum Sellick | 1 | 1 | Done
2 | Create GITHUB Repository. | Kieran Bourne | 1 | 2 | Done
| Incorperate code from Black Board (give to every group) and put it into our repository. | Kieran Bourne & Callum Sellick | 1 | 6 | Done
4 | Add the Sprint plan to the GITHUB Repository. | Callum Sellick | 1 | 0.2 | Done
5 | Create class diagram (UML) | Bogdan-Stefan Pop | 1 | 2 | Done
6 | Create Use-case diagram. | Callum Sellick | 1 | 1 | Done
7 | Create a sequence diagram. | Thomas Hughes | 1 | 2 | Committed
8 | Review Use-case diagram. | Bogdan-Stefan Pop | 1 | 0.1 | Done
9 | Design three tables; customers, admin, drivers. | Kieran Bourne | 1 | 0.2 | Done
10 | Create a JSP basic portal for the admin. | Callum Sellick | 1 | 1 | Committed
11 | Create a basic JSP portal for the driver. | Kieran Bourne | 1 | 1 | Committed
12 | Create a basic JSP portal for customer. | Callum Sellick | 1 | 1 | Committed
13 | Create login page for all users. | Kieran Bourne | 1 | 1 | In-progress
14 | Review class diagram | Callum Sellick | 1 | 1 | Committed
15

## Sprint 2
Backlog - Sprint 2
Duration 12/11/18 To 26/11/18
| Status Levels: | People: | Effort Points |  |  | Individual Hrs: | Group Hrs:
| Committed | Callum Sellick | 1 - Within a day |  |  | 6 hours a week | 24 hrs
| In-progress | Kieran Bourne | 2 - Two days
| Done | Bogdan-Stefan Pop | 3 - More than 2
Thomas Hughes
ID: | Task: | Assigned To: | Effort Points: | Estimated Hours: | Status:
1
2
4
5
6
7
8
9
10
11
12
13
14
15

## Sprint 3
Backlog - Sprint 3
Duration 26/11/18 To 10/12/18
| Status Levels: | People: | Effort Points |  |  | Individual Hrs: | Group Hrs:
| Committed | Callum Sellick | 1 - Within a day |  |  | 6 hours a week | 24 hrs
| In-progress | Kieran Bourne | 2 - Two days
| Done | Bogdan-Stefan Pop | 3 - More than 2
Thomas Hughes
ID: | Task: | Assigned To: | Effort Points: | Estimated Hours: | Status:
1
2
4
5
6
7
8
9
10
11
12
13
14
15