## Sprint 1
Gantt Chart
Duration 29/10/18 To 12/11/18
| Status Levels: | People: | Effort Points | [5 empty] | Individual Hrs: | Group Hrs:
| Committed | Callum Sellick | 1 - Within a day | [5 empty] | 6 hours a week | 24 hrs
| In-progress | Kieran Bourne | 2 - Two days
| Done | Bogdan-Stefan Pop | 3 - More than 2
Thomas Hughes
ID: | Task: | Assigned To: | Effort Points: | Start date: | End Date: | Estimated Days: | Status: | Status % | Hours Done: | Signatures:
1 | Create a sprint document to record progress. | Callum Sellick | 1 | 2018-10-29 | 2018-10-29 | 1 | Done | 100% | 1
2 | Create GITHUB Repository. | Kieran Bourne | 1 | 2018-10-29 | 2018-10-29 | 1 | Done | 100% | 1
3 | Incorperate code from Black Board (give to every group) and put it into our repository. | Kieran Bourne & Callum Sellick | 1 | 2018-10-30 | 2018-10-30 | 1 | Done | 100% | 1
4 | Add the Sprint plan to the GITHUB Repository. | Callum Sellick | 1 | 2018-10-29 | 2018-10-29 | 1 | Done | 100% | 1
5 | Create class diagram (UML) | Bogdan-Stefan Pop | 1 | 2018-11-01 | 2018-11-01 | 1 | Done | 100% | 1
6 | Create Use-case diagram. | Callum Sellick | 1 | 2018-11-01 | 2018-11-01 | 1 | Done | 100% | 1
7 | Create a sequence diagram. | Thomas Hughes | 1 | 2018-11-01 | 2018-11-01 | 1 | Done | 100% | 1
8 | Review Use-case diagram. | Bogdan-Stefan Pop | 1 | 2018-11-01 | 2018-11-01 | 1 | Done | 100% | 1
9 | Design three tables; customers, admin, drivers. | Kieran Bourne | 1 | 2018-11-05 | 2018-11-05 | 1 | Done | 100% | 1
10 | Create portal for users. | Kieran Bourne & Callum Sellick | 1 | 2018-11-06 | 2018-11-06 | 1 | Done | 100% | 1
11 | Create login page for all users. | Kieran Bourne | 1 | 2018-11-06 | 2018-11-06 | 1 | Done | 100% | 1
12 | Review class diagram | Callum Sellick | 1 | 2018-11-01 | 2018-11-01 | 1 | Done | 100% | 1
13 | Create Gantt Chart | Bogdan-Stefan Pop | 1 | 2018-11-11 | 2018-11-11 | 1 | Done | 100% | 1

## Sprint 2
Backlog - Sprint 2
Duration 12/11/18 To 26/11/18
| Status Levels: | People: | Effort Points |  |  |  |  | Individual Hrs: | Group Hrs:
| Committed | Callum Sellick | 1 - Within a day |  |  |  |  | 6 hours a week | 24 hrs
| In-progress | Kieran Bourne | 2 - Two days
| Done | Bogdan-Stefan Pop | 3 - More than 2
Thomas Hughes
ID: | Task: | Assigned To: | Effort Points: | Start date: | End Date: | Estimated Days: | Status: | Status % | Hours Done: | Signatures:
1 | Allow a customer to book a taxi. | Callum Sellick | 1 | 2018-11-12 | 2018-11-12 | 1 | Committed | 100% | 2
2 | Allow admin to view bookings. | Kieran Bourne | 1 | 2018-11-13 | 2018-11-13 | 1 | Committed | 100% | 1
3 | Create version 3 of the class diagram. | Bogdan-Stefan Pop | 1 | 2018-11-14 | 2018-11-14 | 1 | Committed | 0% | 0
4 | Create a Booking table. | Callum Sellick | 1 | 2018-11-14 | 14/11/018 | 1 | Committed | 100% | 1
5 | Create Sprint two tasks. | Callum Sellick | 1 | 2018-11-12 | 2018-11-12 | 1 | In-Progress | 100% | 1
6 | Create customer from bookings. | Kieran Bourne | 1 | 2018-11-13 | 2018-11-14 | 2 | Committed | 0% | 0
7 | Allow drivers to see bookings | Kieran Bourne | 1 | 2018-11-15 | 2018-11-15 | 1 | Committed | 0% | 0
8 | Assign Driver to customer. | Kieran Bourne | 1 | 2018-11-15 | 2018-11-15 | 1 | Committed | 0% | 0
9 | Allow admin to create invoices. | Callum Sellick | 1 | 2018-11-20 | 2018-11-20 | 1 | Committed | 0% | 0
10 | Redesign tables to appear modern | Kieran Bourne | 1 | 2018-11-12 | 2018-11-12 | 1 | Committed | 100% | 1
11 |  |  | 1
12 |  |  | 1
13 |  |  | 1
14 |  |  | 1
15 |  |  | 1

## Sprint 3
Backlog - Sprint 3
Duration 26/11/18 To 10/12/18
| Status Levels: | People: | Effort Points |  |  | Individual Hrs: | Group Hrs:
| Committed | Callum Sellick | 1 - Within a day |  |  | 6 hours a week | 24 hrs
| In-progress | Kieran Bourne | 2 - Two days
| Done | Bogdan-Stefan Pop | 3 - More than 2
Thomas Hughes
ID: | Task: | Assigned To: | Effort Points: | Estimated Hours: | Status:
1
2
4
5
6
7
8
9
10
11
12
13
14
15